## Scrum_03_29_2022
Team Members | What was completed in since last scrum? | What will be completed before the next scrum? | Any impediments?
Tyler Sharkey | UI Mock-ups and Dashboard Front-End | Individual Page Front Ends | N/A
Jonathan Gamble | Finished Dashboard implementation | Deploy Sprint 2 updates to Production Environment | N/A
Alexandria Fuller
Michael Flemens | Updated API to return additional real estate sales data | Test API calls | N/A
Dickson Diku